## Sheet1
| PROJECT NAME | PROJECT DURATION | PROJECT START DATE | PROJECT END DATE
| GameArea |  | April 08, 2021
TASK ID | TASK DESCRIPTION | TASK DURATION | START DATE | END DATE | April 08,2021 | April 09,2021 | April 10,2021 | April 11,2021 | April 12,2021 | April 13,2021 | April 14,2021 | April 15,2021 | April 16,2021 | April 17,2021
1 | Creating Template | 1 | April 08, 2021 | April 09, 2021
2 | Install Dependencies and extension and Creating Repo on github | 1 | April 09, 2021 | April 10, 2021
3 | Implementation Phase 1 - working with story line | 1 | April 10, 2021 | April 11, 2021
4 | Implementation Phase 2 - working with Tic Tac Toe | 1 | April 11, 2021 | April 12, 2021
5 | Creating Github Action | 1 | April 12, 2021 | April 13, 2021
6
7
8 | TESTING
9
10 | Final Testing | 1 | April 16, 2021 | April 17, 2021